COMENIUS 2013-2015

Roads Connecting Us - Connections Between Our Countries and Their Implications in the  Development of the European Integration

ISTITUTO DI ISTRUZIONE SUPERIORE “LEONARDO DA VINCI – CHIAVENNA

The title of the Comenius Project our school is involved in is called: “Roads Connecting Us – Connections Between Our Countries and Their Implications in the  Development of the European Integration”.

Religion, culture, trade and the Exchange of ideas have brought to the setting up of a united Europe. There is quite a number of paths and trails connecting European countries which have contributed to creating international zones and federations. In this multilateral Comenius project we'd like to examine these diverse connections through different kinds of roads in a local and broader context. Starting from our region we are going to examine and perhaps detect hitherto unknown connections between the schools participating and their regions in order to find those elements which represent cultural and social contact points for an effective contribution to the making of a true European integration.

This is the fifth European project in which our school is engaged and in this particular case, of the third multilateral partnership. In the next two years we will work together with four European schools: Gymnasium An der Stenner (Germania);  Suonenjoen Lukio (Finlandia); Colegio Virgen de Mirasierra (Spagna), Katolickie Gimnazjum im. Romualda Traugutta w Chojnicach (Polonia).

We intend to achieve a number of objectives related to the work on the 'roads'-topic itself and to the "Comenius experience" of an inter-European collaboration process and experience. We intend to broaden students' perception of each other by starting from the roads and paths in our cities or regions. They are going to perceive the interconnectedness of their school with the schools in other places and regions.

Furthermore we are intending to apply a historical and geographical perspective too, working on historical paths and their development towards present day paths and roads. We intend to contrast older paths and newer roads. Similarities and differences will also be made clear by including linguistic, literary and other cultural aspects.

Apart from the work on the topic we would like to achieve a higher competence in the use of digital media in general and the use of specific digital cartographic tool (ArgGIS), an enhancement of students' proficiency in English and to develop their intercultural competence and understanding by the work on the different aspects of the roads-topic, by the digital and, not least of all, face-to-face communication on the visits.

With our project we intend to address students' feelings that their region or country is separate from the others, esp. more distant parts of Europe. They will have the opportunity of learning about, and experiencing, aspects of the European development, i.e. enlargement and integration with paths and roads being a fundamental means. Moreover they will have the chance to value other perceptions and insights into life.

One problem we expect is the awareness of the copyright, the awareness of which will be diversely developed among participants. Students will be cautioned to publish self-made materials only, or materials with a Creative Commons License.

We try to achieve our objectives by group work in our home schools, by the digital communication and collaboration between students and teachers, by presenting the results of each project phase in real visits and in offering students the opportunity to visit school lessons at host schools, and to stay in host families - and to host guests - so as to gain direct experience of the other cultures, traditions and values.

We intend to compile and publish all the project results in a digital and (if possible) non-digital book.

The project is directed to 15/16 year-old students, chosen among those attending the third year who in the next two years will work according to these guidelines:

The coordinating school has the main responsibility for the process management of the school partnership. They inform the partners in time, keep contacts, take care that tasks, rights and duties are evenly distributed and propose and carry out adaptations which might be necessary in the course of the project. As for the planning and the execution of the project activities all partners are perfectly equal. Each partner can propose, inform, contact, suggest, exchange information. Every important decision is taken by all partners together.

Every school is responsible for working out of the results of every stage, every country is responsible for the organization of one visit as a host, which includes the preparation and implementation of the specific tasks:

- The school Germany will organize the project meeting "Information about roads - detailed aspects".

- The school Poland will organize the project meeting "Real roads in Past and Present".

- The school Latvia will organize the project meeting "Journeys and Travelling – general perspectives".

- The school Finland will organize the project meeting "Travelling – personal perspective".

- The school Spain will organize the project meeting "Different concepts of roads and travelling in arts in our countries".

- The school Italy will organize the project meeting "Visions of Connecting Europe".

Every school provides uploaded material for the common blog in the 'post-evaluation' phases after each visit.

Apart from these there is a number of tasks that are carried out by every school in consultation with the other partners;

- The school in Spain is responsible for the evaluations at different stages of the project. They are the substitute coordinator for Germany.

- The school in Finland is responsible for creating and coordinating a project blog for the documentation of the work process and the results.

- The school in Italy compiles songs to be included in the final book.

- The schools in Latvia compiles visual elements to be included in the final book.

- The school in Poland compiles literary texts to be included in the final book.

ACTIVITIES 1ST YEAR

| PERIOD | ACTIVITIES |
| --- | --- |
| 09/2013 | Beginning of “Comenius corner”. Project web page; media presence. Selecting students for the project. Setting students tasks connected to the first mobility in Iserlohn. Selecting students taking part in the first mobility in Iserlohn from 15th to 20th December 2013. |
| 10-11-12/2013 | Information about roads – detailed aspects: 1 – Getting to know each other: our ways to school => pictures / films 2 – Road names in our region: road names of our city / region showing cultural aspects, if possible showing connections between our / European countries => drawing / photographing street signs and other relevant information Real roads in Past and Present: 3 – Oldest local trails in our region: places they connected, why and how they were built, their function and what has become of them today => comparative maps: historical vs. modern 4 – Historical long-distance trails passing through our city / region / country: what they connected, how they were built, their function; e.g. the Way of St. James, Hanseatic roads, Amber road, other economic trails) and what has become of them today (e.g. from Roman / Viking camps to cities; from monasteries to economic districts). => Powerpoint presentations and analyses |
| GERMANY 12/2013 | Meeting in Iserlohn: Exchange of results; reports. Journal |
| 01-03/2014 | Preparatory work for the meeting in Poland Journeys and Travelling – general perspectives: - Description of journeys of transporting commodities at 3 different times (e.g. Middle Ages, Cold War, today (including these aspects: infrastructure, supply, risks, road signs, crossing border etc.) - Routes between 2 adjacent countries (Fin <=> Pol <=> Ger <=> Ita <=> Spa) Journeys and Travelling – general perspective: - fictional travel books / log books - creative presentation of interesting episodes - comparing 2 luggage boxes / suitcases of 2 travellers of each country Report (homepage, newspaper, web space) |
| POLAND 04/2014 | Meeting in Chojnice: Exchange of results; reports. Journal |

|  | Participating schools | Country | Town | Website | Contact person |
| --- | --- | --- | --- | --- | --- |
| 1 | Gymnasium An der Stenner | Germany | Iserlohn | http://www.gymnasium-an-der-stenner.de/ | Wolfgang Alkewitz |
| 2 | Suonenjoen lukio | Finland | Suonenjoki | www.peda.net/veraja/suonenjoki/lukio | Anu Liikanen |
| 3 | Colegio Virgen de Mirasierra | Spain | Madrid | www.virgendemirasierra.com | Graciela Hernando |
| 4 | Katolickie Gimnazjum im. Romualda Traugutta w Chojnicach | Poland | Chojnice | www.katolik.chojnice.pl | Rafal Maliszewski |
| 5 | IIS "Leonardo da Vinci"di Chiavenna | Italy | Chiavenna | www.davincichiavenna.it | Marco Del Papa |